## Estimates(DEV)
Component | Type | Stories | Description | ABP | HP | Effort | Comments
Document Configurator | Design | Schema Design | To design schema to s | 10 | 15 | 12.5 | GraphDB may be to define relation between nodes
| Front End | React Set up |  | 10 | 15 | 12.5
| Front End | React Graph Configurator Design |  | 10 | 15 | 12.5
| Front End | React graph List |  | 10 | 15 | 12.5
|  | Create New graph |  | 20 | 30 | 25
|  | Edit Graph |  | 10 | 50 | 30
| API | Add New Configuration |  | 20 | 25 | 22.5
|  | Load Configuration |  | 15 | 20 | 17.5
|  | Save Configuration |  | 20 | 25 | 22.5
|  | Set up/Design |  | 15 | 20 | 17.5
Rules Designer | Front End | Load Configuration defined by configurator |  | 20 | 30 | 25
| Front End | Define Rules on Nodes/Facts defined in configurator |  | 40 | 50 | 45
| API | Handling API operations | orchestrating rules | 30 | 40 | 35
Rules Executor |  | Execution of rules |  | 60 | 80 | 70 | Adjsut depending on If we go with Drool Fusion
Rule Visualizer | Front End | View Dry run of rules |  | 20 | 30 | 25 | For dry running rules
| API |  |  | 40 | 50 | 45 | Adjsut depending on If we go with Drool Fusion
Recorder |  | For recording at run time which path for rules was taken | providing telemetry into rules | 20 | 30 | 25
|  |  |  | 370 | 540 | 455
IF we go with drool rules part we can replace with integration with configurator